## ITP Template
Inspection and Test Plan
Contract Name: |  |  | Contract Number: |  | Revision Number: |  |  |  |  | 0 |  |  | m | Alternative
Activity: | Electrical Installations |  | Date: |  | I = In-process Inspection – Work Continues, record made | [7 empty] | l | Person responsible
Prepared by: |  |  | Signature: |  | W = Witness Inspection – Work Continues – Signature of Witness,
Approved by: |  |  | Signature: |  | H = Hold Point – Stop work until seen – Signed Record
RESPONSIBILITY
WORK / ACTIVITY | REFERENCES | INSPECTION / TEST | FREQUENCY | ACCEPTANCE CRITERIA | HOLD POINTS | C.M. | Electrical Design Engineer | Electrical Project Engineer | Electrical Site Supervisor | Electrician | S/C | CLIENT | VERIFICATION DOCUMENTS | COMMENTS
Example: setting-out | CESWI 7th edition Cl. 1.8 | closing errors on survey stations (contract and additional) | start of contract & as further stations are needed | angle +/-(10√N)"; distance +/-1/10000; level +/-(12√K)mm (for K km of traverse) | I |  | m | l |  |  |  |  | Setting out check list CF322-204, Survey book | distribute acceptable error; re-survey if un-acceptable
Prestart Activities
Scoping the task | Client requirements | Tests (essential elements) are found in the scoping tool | Each task | Completed Scoping Tool | H |  | m | m |  | l | m |  | Scoping Tool document; Client Work Management System
Design | Client requirements; Water Industry Mechanical and Electrical Specifications (WIMES) Cl. 6.0 - 6.2; BSEN 61439-2:2011 Cl. 10 | Tests (essential elements) are found in the scoping tool | Each task | Completed Scoping Tool | H |  | l | m |  |  |  |  | Single line diagram; Block cable diagram; Panel schematic; Load schedule; Cable schedule; Termination detail
Materials procurement | Single line diagram; Block cable diagram; Panel schematic; Load schedule; Cable schedule; Termination detail | Checked against: Single line diagram; Block cable diagram; Panel schematic; Load schedule; Cable schedule; Termination detail | Each task | 100% | I |  |  |  |  | l |  |  | Purchase order
Materials approval | Specification (e.g. CESWI 7th edition), Drawings | Designer approval | Each permanent works material Monitor deliveries | To be completed | H |  |  | m | m | l |  |  | Materials approval form; Certificates of conformity | example; pipe and fittings, bedding, backfill.
In process Activities
Receiving materials | Specification (e.g. CESWI 7th edition), Drawings | Visual inspection | To be completed | To be completed | H |  |  | m |  | l | m |  | Materials traceability record - CF322-60
Electrical assembly & Inspection and Testing | WIMES Cl. 6.3 - 6.8 | Checked against: Single line diagram; Block cable diagram; Panel schematic; Load schedule; Cable schedule; Termination detail | Each task | 100% | H |  |  |  |  | m | l |  | Electrical installation certificate; Electrical installation condition report; Minor electrical installation works;
Intelligent Assembly (PLC) | WIMES Cl. 6.9; Manufacturers specifications; Client specifications |  | Each task | 100% | H |  |  | m |  | m |  | l | Functionality report
Commissioning | WIMES Cl. 7.0 - 7.5 | Checked against: Single line diagram; Block cable diagram; Panel schematic; Load schedule; Cable schedule; Termination detail | Each task | 100% | H |  |  | m |  | l | m |  | Commissioning Record - CF322-427
Appointed Person Check | Single line diagram; Block cable diagram; Panel schematic; Load schedule; Cable schedule; Termination detail | Checked against: Single line diagram; Block cable diagram; Panel schematic; Load schedule; Cable schedule; Termination detail | Each task | 100% | H |  | m |  |  | l |  |  | Red line drawings
Handover | Electrical cabling design schematic diagram; Client specifications |  |  | 100% | H | l |  | m |  |  |  |  | Client acceptance; Operation and Maintenance Manual
Records
Close out all NCR's | NCR Procedure |  | As required | Close out all NCR actions | H |  | l | [5 empty] | NCR's | Close out in line with construction process. Agree remedial actions close out with design team.
As-built records | Project Quality Plan |  | Each completed structure/element. | Signed off as-built record pack. | H |  |  | l |  |  |  |  | As-built package | Review and sign off.
As-built drawings | Project Quality Plan |  | Each completed structure/element. | Signed off as-built drawings | H |  |  | l |  |  |  |  | As-built drawings | Review and sign off.