## ITP Template
Inspection and Test Plan
Client |  |  | Contract |  | Revision Number
Activity | Site Installation |  | Date |  |  | l | Person responsible |  |  | m | Alternative
Prepared by |  |  | Signature |  |  | I = In-process Inspection – Work Continues, record made
Approved by |  |  | Signature |  |  | W = Witness Inspection – Work Continues – Signature of Witness,
H = Hold Point – Stop work until seen – Signed Record
RESPONSIBILITY
WORK / ACTIVITY | REFERENCES | INSPECTION / TEST | FREQUENCY | ACCEPTANCE CRITERIA | HOLD POINTS | C.M. | AGENT | ENGINEER | SITE BLACKHAT | INSTALLATION TEAM | CLIENT | VERIFICATION DOCUMENTS | COMMENTS
Example: setting-out | CESWI7 cl1.8 | closing errors on survey stations (contract and additional) | start of contract & as further stations are needed | angle +/-(10√N)"; distance +/-1/10000; level +/-(12√K)mm (for K km of traverse) | I |  | m | l |  |  |  | Setting out check list CF322-204, Survey book | distribute acceptable error; re-survey if un-acceptable
Employee competence checks | CSCS, SSSTS, PTS and CPI. Site specifications | Visual inspection | Once | Meets code specifications | H | m | l | l |  |  |  | Inspection checklist CF450-69
Approve safe systems of work | RAMS | Approval | Once | Meets specification | H | m | l | l |  |  |  | Risk Assessment & Method Statement CF621-50
Carry out inspection of site access prior to installation | n/a | Visual inspection | Once | n/a | I |  |  |  |  | l
Receive delivery of materials on site | Installation drawing / Inspection checklist | Visual inspection | Each delivery | 100% correct to drawing / specifications | I |  |  |  | m | l |  | Delivery paperwork. Inspection checklist CF450-69
Tools serviced / calibrated | Manufacturers guidance / CG686-01 | Visual inspection | As per guidance | As per guidance | I |  |  |  | m | l |  | Calibration certificates / PAT test certificates.
Intsall asset | Drawings and RAMS | Visual inspection | Every structure | Every structure | I |  |  |  |  | l |  | Inspection checklist CF450-69
Nuts / bolts tight | Drawing | Physical check | Every nut and bolt | All in place to correct tightness | I |  |  |  | m | l |  | Inspection checklist CF450-69
Coating and quality check | Drawing | Visual inspection | Every structure | Identify all abnormalities | I |  |  |  | m | l |  | Inspection checklist CF450-69 Photographs.
Final sign off | Drawing | Visual inspection | Every structure | ID all rework and confirm levels | H | m | l | m | m |  | m | Inspection checklist CF450-69